## County Level Monitoring Temp
Region | Counties
Nairobi | Nairobi
Coast Region | Mombasa
Kwale
Kilifi
Lamu
Tana River
Taita Taveta
TOTAL | 7
Sub County Name: |  | Targets | Indicators | Time Frame (2013) | [5 empty] | Responsible Person |  |  | Notes
Objectives | Activities |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Name | Email | Phone
Ensure providers (public and private) appropriately assess and treat children suffering from diarrhoea with Zinc and ORS as the first line treatment | Conduct baseline assessment |  | % of facilities assessed and analytics disseminated
| Orientation of sub-county HCWs on diarrhoea policy & guidelines |  | % of facilities with at least one HCWs oriented on diarrhoea policy and guidelines
| Identify HCWS to be trained from facilities in the county |  | # of health care workers needing IMCI training
| Roll out IMCI trainings (With national support) |  | % of faciliites with at least two HCWs trained on IMCI
| Roll out diarrhoea management CMEs in all facilities (CME package to be developed at national level) |  | % of facilities where diarrhoea specific CMEs have been rolled out
| Train a pool of "diarrhoea case management" mentors |  | # of diarrhoea management mentors trained
| Mentor HCWs on diarrhoea case management in all health facilities |  | % of facilities identified for mentoring and mentored
| Conduct an ORT Corners assessment |  | % of facilities without functional ORT corners
| Support the set up of ORT corners in all facilities |  | % of facilities supported in setting up functional ORT Corners
| Ensure all facilities have ORT corner operational guidelines and registers (Distribution) |  | % of facilities with ORT operational guidelines, % with ORT Corner registers..
| Ensure all facilities have diarrhoea management algorithm (job aid - Distribution) |  | % of facilities with diarrhoea management algorithm (job aid)
| Ensure all facilities have adequate copies of IMCI chart booklets (Distribution) |  | % of facilities with IMCI chart booklets
| Introduce & support the roll out of standardized diarrhoea health talks in all facilities (health talk kits to be provided) |  | % of facilities actively providing diarrhoea health talks at least twice a week
| Introduce and support the roll out of diarrhoea management documentary (to be developed at national level) in all health facilities |  | % of facilities actively displaying diarrhoea management documentary...
Increase proximity of care to the 40% of caregivers that stay at home | Train a pool of CHEWs as Trainers for Integrated Community Case Management (ICCM) |  | % of CHEWS trained as ICCM TOTs
| Roll out ICCM training to active CHWs from functional Community Units |  | % of CHWs trained on ICCM
| Provide trained CHEWS/CHWS with IEC materials & Job aids on ICCM (to be developed at national level) |  | % of community units supported with IEC materials, job aids on ICCM
| Work with implementing partners to reactivate semi and non-functional community units |  | % of community units reactivated
| Conduct quarterly community outreaches in all facilities which includes diarrhoea specific messaging and activities |  | % of quartely community outreaches conducted
| Support community units to conduct intensive household visits during outreach week |  | % of households visited during outreach week
Increase availability of ZN/ORS in the public sector | Ensure facilities have zero stock out of zinc in at least 6 consequtive months |  | % of facilities with zero stock out of zinc in the last 6 months
| Ensure facilities have zero stock out of ORS in at least 6 consequtive months |  | % of facilities with zer stock out of ORS in the last 6 months
| Manually bundle existing stocks of Zinc and ORS(4 sachets of ORS + 10 Tablets of Zinc sulphate) in all facilities |  | % of facilities manually bundling Zinc and ORS
| Ensure the zinc/ORS co-pack is available in all facilities |  | % of facilities with co-pack stocked with 'co-pack'
| Ensure the ZINC/ORS co-pack is available in all the active community units |  | % of active community units served with 'co-packs' (Zinc and ORS) for ICCM
| Roll out HCMP in facilities (on-going with DPFs) |  | % of facilities actively utilizing HCMP for commodity management
Monitoring of activities | Conduct supportive supervision in all health facilities |  | % of facilities regularly supervised on IMCI and provided feedback

## Private Sector Indicators
Private Sector Partners
Clinton health access initiative
PSI-Population Service Internatiional
MI-Micronutrient initiative
Cosmos Pharmaceutical Itd
Universal Corperation
Phillips Health Care Services Ltd
SHOPS-Strengthening Heatlth Outcomes through the Private Sector
MEDS-Mission for Essential Drugs and Supplies
OBJECTIVES | ACTIVITIES | KPIs | REPRTING PARTNERS
Commodity Availability | Recruitment of Distributers and Retaillers | No.of Distributers and Retaillers recruited/buying/stocking the commodity and their names. | PHSL,COSMOS and PSI
Awareness | Ethical awareness trainings,detailing, | No. of CMEs in a month,no.of facilities reached,no. of particpants raeched and their identity/category/ | PHSL,COSMOS and PSI
Follow up on awareness activities | One on one follow up calls on those reached by CMEs,Physical visits to those trained in CMEs | No. of follow ups made on those reached by CMEs | PHSL,COSMOS and PSI
Ethical Detailing | Deploy a detailing team,Training the team,Visits by the detailing team to Pedeatricians,COs,Pharmacies, etc | No. of detailers,no of trained detailers,no of trainings done for the detailers,no of visits by detailers by category i.e. GPs,Peads, C.O.s,Chemists etc. | PHSL,COSMOS and PSI
Conduct Promotional Activities | Run radio adds,Road shows,Medical camps,shop to shop campaigns, | No of activities conducted | PHSL,COSMOS and PSI
Distribution of protional materials | Issuing of distribution materials to doctors,C.O.s,Pharmacies etc | No of promotional materials used per category and no of persons issued with promotional materials per category i.e. pedeatritians,GPs,C.O.s | PHSL,COSMOS and PSI
Participation in professional forums |  | No. of proffessinal forums attended | PHSL,COSMOS and PSI
Reach all the regions by marketing and detailing activities |  | No. of counties covered by detaillers,No of counties reached by the co-pack | PHSL,COSMOS and PSI
Monitor sales |  | Quantities sold, quanties re-ordered per outlet category and stock levels | PHSL,COSMOS and PSI
Work with CBOs | Recruit CBOs into the distribution chain | No of CBOs recruited,No of packs sold to CBOs | PHSL,COSMOS, CHAI,and PSI